## User Stories
ID | Story Title | Points | Priority | As a/an [user] | I want [functionality] | So that [value] | User Story | NFR | Definition of Done / Blockers | Epic ID | Status | Notes
S1 | login and logout | 8 | High | registered player | to log in and out | i can use my account | as a registered player, i want to log in and out, so that i can use my account. | NFR1, NFR7, NFR10 | done when users can log in and log out and bad logins dont work. | E1 | Open | original priority: must ¦ release: mvp ¦ effort: ≈ crud
S2 | make an account | 8 | High | new player | to register with my email username and password | my progress can be saved | as a new player, i want to register with my email username and password, so that my progress can be saved. | NFR1, NFR7, NFR10 | done when users can make an account and usernames have to be different. | E1 | Open | original priority: must ¦ release: mvp ¦ effort: ≈ crud
S3 | see the disclaimer | 3 | High | player | to see and accept the play money disclaimer | i know what the game is | as a player, i want to see and accept the play money disclaimer, so that i know what the game is. | NFR9, NFR10 | done when users have to accept the disclaimer before playing. | E2 | Open | original priority: must ¦ release: mvp ¦ effort: much simpler than crud
S4 | play as a guest | 5 | High | guest | to play without making an account | i can try the game right away | as a guest, i want to play without making an account, so that i can try the game right away. | NFR7, NFR9, NFR10 | done when guests can pick a name and avatar without making an account. | E3 | Open | original priority: must ¦ release: mvp ¦ effort: simpler than crud
S5 | pick an avatar | 5 | Medium | registered player | to pick an avatar | i can make my profile look how i want | as a registered player, i want to pick an avatar, so that i can make my profile look how i want. | NFR7, NFR9, NFR10 | done when players can pick an avatar and save it. | E4 | Open | original priority: should ¦ release: mvp ¦ effort: simpler than crud
S6 | play texas holdem | 21 | High | player | the texas holdem game to work correctly | i can play a normal poker game | as a player, i want the texas holdem game to work correctly, so that i can play a normal poker game. | NFR8, NFR9, NFR10 | done when poker should work like normal poker with betting and winners. | E5 | Open | original priority: must ¦ release: mvp ¦ effort: far more complex than crud
S7 | see my poker hand | 8 | High | player | to see what poker hand i have | i know how good my hand is | as a player, i want to see what poker hand i have, so that i know how good my hand is. | NFR8, NFR9, NFR10 | done when the game should show what poker hand the player has. | E5 | Open | original priority: must ¦ release: mvp ¦ effort: ≈ crud overall
S8 | see poker rules | 5 | Medium | new player | to see the rules and hand rankings | i can learn how to play | as a new player, i want to see the rules and hand rankings, so that i can learn how to play. | NFR9, NFR10 | done when there should be a rules page that explains poker. | E6 | Open | original priority: should ¦ release: mvp ¦ effort: simpler than crud
S9 | get hints | 13 | Low | new player | to turn hints on and off | i can understand what moves i can make | as a new player, i want to turn hints on and off, so that i can understand what moves i can make. | NFR9, NFR10 | done when players can turn hints on or off. | E6 | Open | original priority: could ¦ release: phase 2 ¦ effort: more complex than crud
S10 | browse public tables | 13 | High | player | to see public tables | i can find a game to join | as a player, i want to see public tables, so that i can find a game to join. | NFR3, NFR5, NFR9, NFR10 | done when players can see public poker tables in the lobby. | E7 | Open | original priority: must ¦ release: mvp ¦ effort: more complex than crud
S11 | filter tables | 8 | Medium | player | to filter the table list | i can find the kind of game i want | as a player, i want to filter the table list, so that i can find the kind of game i want. | NFR5, NFR9, NFR10 | done when players can use filters to find tables. | E7 | Open | original priority: should ¦ release: mvp ¦ effort: ≈ crud
S12 | live game updates | 21 | High | live player | the game to update live for everyone | everyone sees the same game | as a live player, i want the game to update live for everyone, so that everyone sees the same game. | NFR3, NFR4, NFR5, NFR8, NFR10 | done when the game should stay synced for all players. | E8 | Open | original priority: must ¦ release: mvp ¦ effort: far more complex than crud
S13 | make a public table | 13 | High | host | to create a public table | other players can join my game | as a host, i want to create a public table, so that other players can join my game. | NFR5, NFR9, NFR10, NFR11 | done when hosts can make a table and choose the settings. | E9 | Open | original priority: must ¦ release: mvp ¦ effort: more complex than crud
S14 | get starting chips | 5 | High | new registered player | to start with 1,000 virtual chips | i can join a beginner table | as a new registered player, i want to start with 1,000 virtual chips, so that i can join a beginner table. | NFR6, NFR11 | done when new accounts get 1,000 fake chips. | E10 | Open | original priority: must ¦ release: mvp ¦ effort: simpler than crud
S15 | check table buy in | 5 | High | player | the game to stop me from joining if i dont have enough chips | table buy ins are followed | as a player, i want the game to stop me from joining if i dont have enough chips, so that table buy ins are followed. | NFR6, NFR9 | done when players need enough chips to join a table. | E10 | Open | original priority: must ¦ release: mvp ¦ effort: simpler than crud
S16 | save chip balance | 13 | High | player | my chip wins and losses to save | my balance stays correct | as a player, i want my chip wins and losses to save, so that my balance stays correct. | NFR4, NFR6, NFR11 | done when chip balances should update correctly. | E10 | Open | original priority: must ¦ release: mvp ¦ effort: more complex than crud
S17 | see my stats | 8 | Medium | registered player | to see my poker stats | i can see how i am doing | as a registered player, i want to see my poker stats, so that i can see how i am doing. | NFR7, NFR11 | done when players can see their poker stats. | E11 | Open | original priority: should ¦ release: mvp ¦ effort: ≈ crud
S18 | see the leaderboard | 13 | High | player | to see a leaderboard | i can compare myself to other players | as a player, i want to see a leaderboard, so that i can compare myself to other players. | NFR6, NFR7, NFR11 | done when there should be a leaderboard for players. | E12 | Open | original priority: must ¦ release: mvp ¦ effort: more complex than crud
S19 | add and remove friends | 8 | Medium | registered player | to add and remove friends | i can keep a list of people i play with | as a registered player, i want to add and remove friends, so that i can keep a list of people i play with. | NFR7, NFR11 | done when players can add and remove friends. | E13 | Open | original priority: should ¦ release: mvp ¦ effort: ≈ crud
S20 | see friends online | 13 | Medium | player | to see which friends are online or at a table | i can find and play with them | as a player, i want to see which friends are online or at a table, so that i can find and play with them. | NFR3, NFR7, NFR11 | done when players can see if their friends are online. | E13 | Open | original priority: should ¦ release: mvp ¦ effort: more complex than crud
S21 | message other players | 13 | Medium | player | to message friends and people at my table | i can talk to people while playing | as a player, i want to message friends and people at my table, so that i can talk to people while playing. | NFR3, NFR7, NFR10, NFR11 | done when players can message friends and use table chat. | E14 | Open | original priority: should ¦ release: mvp ¦ effort: more complex than crud
S22 | handle afk players | 13 | High | active player | inactive players to get sat out or removed | the game does not get stuck | as a active player, i want inactive players to get sat out or removed, so that the game does not get stuck. | NFR3, NFR5, NFR9, NFR11 | done when players can be marked afk if they dont do anything. | E15 | Open | original priority: must ¦ release: mvp ¦ effort: more complex than crud
S23 | clean up empty tables | 8 | Medium | administrator | empty or inactive tables to get cleaned up | the lobby does not fill with old tables | as a administrator, i want empty or inactive tables to get cleaned up, so that the lobby does not fill with old tables. | NFR5, NFR11 | done when old empty tables should eventually get deleted. | E15 | Open | original priority: should ¦ release: mvp ¦ effort: ≈ crud
S24 | fill seats with bots | 21 | Medium | player | bots to fill empty seats | i can play when not enough people are online | as a player, i want bots to fill empty seats, so that i can play when not enough people are online. | NFR5, NFR8, NFR11 | done when bots can play poker and make legal moves. | E16 | Open | original priority: should ¦ release: mvp ¦ effort: far more complex than crud
S25 | play only bots | 13 | Medium | host | to make a table with only bots | i can practice by myself | as a host, i want to make a table with only bots, so that i can practice by myself. | NFR8, NFR9, NFR10 | done when players can start games with bots. | E16 | Open | original priority: should ¦ release: mvp ¦ effort: more complex than crud
S26 | watch a game | 13 | Low | user | to watch a table without taking a seat | i can watch friends or learn | as a user, i want to watch a table without taking a seat, so that i can watch friends or learn. | NFR7, NFR9, NFR10 | done when people can watch games without playing. | E17 | Open | original priority: could ¦ release: phase 2 ¦ effort: more complex than crud
S27 | make a private table | 13 | Low | host | to make a private table and invite friends | only invited people can join | as a host, i want to make a private table and invite friends, so that only invited people can join. | NFR1, NFR2, NFR7, NFR11 | done when private tables need an invite to join. | E18 | Open | original priority: could ¦ release: phase 2 ¦ effort: more complex than crud
S28 | manage users and tables | 21 | High | administrator | to manage users tables and games | i can moderate the app | as a administrator, i want to manage users tables and games, so that i can moderate the app. | NFR2, NFR7, NFR11 | done when admins can view users and tables and moderate things. | E19 | Open | original priority: must ¦ release: mvp ¦ effort: far more complex than crud
S29 | get daily chips | 8 | Low | registered player | to get a daily chip reward | i can keep playing after losing chips | as a registered player, i want to get a daily chip reward, so that i can keep playing after losing chips. | NFR6, NFR11 | done when players can claim free chips sometimes. | E20 | Open | original priority: could ¦ release: phase 2 ¦ effort: ≈ crud
S30 | get chips from ads | 13 | Low | player | to get chips for watching an ad | i can refill my chip balance | as a player, i want to get chips for watching an ad, so that i can refill my chip balance. | NFR6, NFR11 | done when players can get chips after watching an ad. | E21 | Open | original priority: could ¦ release: phase 2 ¦ effort: more complex than crud
S31 | buy virtual chips | 21 | Low | registered player | to buy virtual chips | i can keep playing higher buy in games | as a registered player, i want to buy virtual chips, so that i can keep playing higher buy in games. | NFR6, NFR7, NFR11 | done when players can buy fake chips but cant turn them into real money. | E21 | Open | original priority: could ¦ release: phase 2 ¦ effort: far more complex than crud
S32 | earn xp and achievements | 13 | Low | registered player | to earn xp and achievements | i have goals to work toward | as a registered player, i want to earn xp and achievements, so that i have goals to work toward. | NFR6, NFR11 | done when players can earn xp and achievements. | E22 | Open | original priority: could ¦ release: phase 2 ¦ effort: more complex than crud
S33 | seasonal leaderboards | 13 | Low | competitive player | leaderboards to reset by season | there is new competition | as a competitive player, i want leaderboards to reset by season, so that there is new competition. | NFR6, NFR11 | done when the game can have different seasons. | E12 | Open | original priority: could ¦ release: phase 2 ¦ effort: more complex than crud
S34 | choose bot difficulty | 21 | Low | player | to choose how hard the bots are | i can practice at different levels | as a player, i want to choose how hard the bots are, so that i can practice at different levels. | NFR8, NFR9 | done when bots can have different difficulty levels. | E16 | Open | original priority: could ¦ release: later ¦ effort: far more complex than crud
S35 | change the theme | 5 | Low | player | to change the game theme | i can change how the game looks | as a player, i want to change the game theme, so that i can change how the game looks. | NFR9, NFR10 | done when players can pick different themes. | E23 | Open | original priority: could ¦ release: later ¦ effort: simpler than crud
S36 | join tournaments | 21 | Low | player | to join poker tournaments | i can play through elimination rounds | as a player, i want to join poker tournaments, so that i can play through elimination rounds. | NFR5, NFR6, NFR8, NFR11 | done when tournaments should work with blinds, eliminations, and winners. | E24 | Open | original priority: could ¦ release: later ¦ effort: far more complex than crud
S37 | use a bot api | 21 | Low | authorized developer | to use a documented bot api | approved bots can join allowed games | as a authorized developer, i want to use a documented bot api, so that approved bots can join allowed games. | NFR1, NFR2, NFR5, NFR8, NFR11 | done when the api should require login and have rules for how it can be used. | E25 | Open | original priority: could ¦ release: later ¦ effort: far more complex than crud

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description
E1 | Accounts | account registration login and logout
E2 | Age / Legal | the play money and age disclaimer
E3 | Guest Play | letting people try the game without an account
E4 | Profiles | player profiles and avatar choices
E5 | Poker Engine | the main texas holdem rules betting and hand logic
E6 | Learning | rules hand rankings and player hints
E7 | Lobby | finding and filtering public poker tables
E8 | Multiplayer | keeping online players and game state synced
E9 | Tables | creating public poker tables and table settings
E10 | Bankroll | virtual chip balances buy ins wins and losses
E11 | Statistics | tracking player poker statistics
E12 | Leaderboard | ranking players and seasonal competition
E13 | Social | friends and online status
E14 | Messaging | friend messages and table chat
E15 | AFK / Lobby | handling inactive players and abandoned tables
E16 | Bots | computer poker players and bot games
E17 | Spectator | watching games without taking a seat
E18 | Private Tables | invite only poker tables
E19 | Administration | admin moderation and game management
E20 | Rewards | free virtual chip rewards
E21 | Monetization | rewarded ads and virtual chip purchases
E22 | Progression | xp achievements and long term progress
E23 | Customization | table and background themes
E24 | Tournament | tournament style poker games
E25 | Developer Platform | approved developer access for external poker bots

## NFR
ID | Title | Category | Description | Affects
1 | Security | Security | Passwords and authentication data must be protected using modern secure practices, and all authenticated traffic must use encrypted HTTPS connections. verification: Security review confirms hashed/salted password storage, secure session handling, and HTTPS-only authenticated traffic. | Accounts, Private Tables, Developer Platform
2 | Authorization | Authorization | Administrative functions must use role-based access control so that non-admin users cannot perform moderation or game-management actions. verification: Authorization tests confirm protected admin endpoints reject normal and guest users. | Administration, Private Tables, Developer Platform
3 | Performance | Performance | For an active poker table under normal load, player actions should be reflected to connected players within 500 ms for at least 95% of actions, excluding client internet latency outside the service. verification: Load test records server-side action-to-broadcast latency and confirms the 95th percentile target. | Multiplayer, Messaging, Social
4 | Availability / Recovery | Availability / Recovery | The application must preserve authoritative game state so that a brief client disconnect does not corrupt a hand and a reconnecting player can recover the current table state. verification: Disconnect/reconnect tests during each betting round recover the correct current hand and player state. | Multiplayer, Bankroll
5 | Scalability | Scalability | The architecture must support horizontal scaling of public lobbies, chat/presence, and concurrent poker tables without requiring a redesign of the core domain model. verification: Architecture review and load tests demonstrate multiple application instances can share authoritative state safely. | Lobby, Multiplayer, Tables, Messaging, Bots, Tournament
6 | Data Integrity | Data Integrity | Virtual-chip transactions and pot payouts must be atomic and auditable so that retries, refreshes, or duplicate requests cannot create or destroy chips incorrectly. verification: Automated tests verify idempotent transactions and that total debits/credits reconcile after completed hands. | Bankroll, Rewards, Monetization, Tournament
7 | Privacy | Privacy | The system must collect only information needed for accounts and gameplay, and personal account data must not be exposed to other players beyond approved profile fields. verification: Privacy review verifies email and authentication data are not returned in public profile, lobby, chat, or leaderboard responses. | Accounts, Profiles, Statistics, Leaderboard, Social, Messaging
8 | Anti-Cheat / Fairness | Anti-Cheat / Fairness | The server must be authoritative for card dealing, deck state, legal actions, turn order, and outcomes so clients cannot choose cards or submit impossible game actions. verification: Tampered-client tests confirm invalid actions are rejected and hidden card/deck state is not exposed. | Poker Engine, Bots, Tournament, Developer Platform
9 | Usability / Accessibility | Usability / Accessibility | Core gameplay, lobby, account, and navigation controls must be keyboard accessible and provide sufficient text labels/contrast for common accessibility needs. verification: Accessibility review checks keyboard navigation, visible focus, semantic labels, and WCAG 2.1 AA contrast for core screens. | All
10 | Compatibility / Responsive Design | Compatibility / Responsive Design | The web app must be usable on current major desktop browsers and adapt to common laptop, tablet, and mobile browser widths without blocking core gameplay controls. verification: Cross-browser/responsive test covers current Chrome, Edge, Firefox, and Safari plus representative mobile widths. | All
11 | Maintainability / Observability | Maintainability / Observability | The production system must record structured logs and key operational metrics for authentication failures, table creation, game errors, disconnects, and administrative actions without logging passwords or hidden-card secrets. verification: Operational review confirms required events/metrics exist and sensitive fields are excluded from logs. | All