## User Stories
ID | Story Title | Points | Priority | As a/an [user] | I want [functionality] | So that [value] | User Story | NFR | Definition of Done / Blockers | Epic ID | Status | Notes
S1 | login and logout | 1 | High | registered player | to log in and out | i can use my account | as a registered player, i want to log in and out, so that i can use my account. | NFR1, NFR7, NFR10 | done when users can log in and log out | E1 | Open
S2 | make an account | 2 | High | new player | to register with my email username and password | my progress can be saved | as a new player, i want to register with my email username and password, so that my progress can be saved. | NFR1, NFR7, NFR10 | done when users can make an account and usernames are different | E1 | Open
S3 | see the disclaimer | -- |  | player | to see and accept the play money disclaimer | i know what the game is | as a player, i want to see and accept the play money disclaimer, so that i know what the game is. | NFR9, NFR10 | done when users have to accept the disclaimer before playing. | E2 | Open
S4 | play as a guest | 1 | Low | guest | to play without making an account | i can try the game right away | as a guest, i want to play without making an account, so that i can try the game right away. | NFR7, NFR9, NFR10 | done when guests can pick a name without making an account. | E3 | Open
S5 | pick an avatar | 3 | Medium | registered player | to pick an avatar | i can make my profile look how i want | as a registered player, i want to pick an avatar, so that i can make my profile look how i want. | NFR7, NFR9, NFR10 | done when players can pick an avatar and save it. | E4 | Open
S6 | play texas holdem | 13 | High | player | the texas holdem game to work correctly | i can play a normal poker game | as a player, i want the texas holdem game to work correctly, so that i can play a normal poker game. | NFR8, NFR9, NFR10 | done when poker should work like normal poker with betting and winners. | E5 | Open
S7 | see my poker hand | 1 | High | player | to see what poker hand i have | i know how good my hand is | as a player, i want to see what poker hand i have, so that i know how good my hand is. | NFR8, NFR9, NFR10 | done when the game should show what poker hand the player has. | E5 | Open
S8 | see poker rules | -- | Medium | new player | to see the rules and hand rankings | i can learn how to play | as a new player, i want to see the rules and hand rankings, so that i can learn how to play. | NFR9, NFR10 | done when there should be a rules page that explains poker. | E6 | Open
S9 | get hints | 3 | Low | new player | to turn hints on and off | i can understand what moves i can make | as a new player, i want to turn hints on and off, so that i can understand what moves i can make. | NFR9, NFR10 | done when players can turn hints on or off. | E6 | Open
S10 | browse public tables | 2 | High | player | to see public tables | i can find a game to join | as a player, i want to see public tables, so that i can find a game to join. | NFR3, NFR5, NFR9, NFR10 | done when players can see public poker tables in the lobby. | E7 | Open
S11 | filter tables | 1 | Medium | player | to filter the table list | i can find the kind of game i want | as a player, i want to filter the table list, so that i can find the kind of game i want. | NFR5, NFR9, NFR10 | done when players can use filters to find tables. | E7 | Open
S12 | live game updates | -- | High | live player | the game to update live for everyone | everyone sees the same game | as a live player, i want the game to update live for everyone, so that everyone sees the same game. | NFR3, NFR4, NFR5, NFR8, NFR10 | done when the game should stay synced for all players. | E8 | Open
S13 | make a public table | 2 | High | host | to create a public table | other players can join my game | as a host, i want to create a public table, so that other players can join my game. | NFR5, NFR9, NFR10, NFR11 | done when hosts can make a table and choose the settings. | E9 | Open
S14 | get starting chips | -- | High | new registered player | to start with 1,000 virtual chips | i can join a beginner table | as a new registered player, i want to start with 1,000 virtual chips, so that i can join a beginner table. | NFR6, NFR11 | done when new accounts get 1,000 fake chips. | E10 | Open
S15 | check table buy in | 1 | Low | player | the game to stop me from joining if i dont have enough chips | table buy ins are followed | as a player, i want the game to stop me from joining if i dont have enough chips, so that table buy ins are followed. | NFR6, NFR9 | done when players need enough chips to join a table. | E10 | Open
S16 | save chip balance | 2 | High | player | my chip wins and losses to save | my balance stays correct | as a player, i want my chip wins and losses to save, so that my balance stays correct. | NFR4, NFR6, NFR11 | done when chip balances should update correctly. | E10 | Open
S17 | see my stats | 1 | Medium | registered player | to see my poker stats | i can see how i am doing | as a registered player, i want to see my poker stats, so that i can see how i am doing. | NFR7, NFR11 | done when players can see their poker stats. | E11 | Open
S18 | see the leaderboard | 1 | High | player | to see a leaderboard | i can compare myself to other players | as a player, i want to see a leaderboard, so that i can compare myself to other players. | NFR6, NFR7, NFR11 | done when there should be a leaderboard for players. | E12 | Open
S19 | add and remove friends | 5 | Medium | registered player | to add and remove friends | i can keep a list of people i play with | as a registered player, i want to add and remove friends, so that i can keep a list of people i play with. | NFR7, NFR11 | done when players can add and remove friends. | E13 | Open
S20 | see friends online | 3 | Medium | player | to see which friends are online or at a table | i can find and play with them | as a player, i want to see which friends are online or at a table, so that i can find and play with them. | NFR3, NFR7, NFR11 | done when players can see if their friends are online. | E13 | Open
S21 | message other players | 8 | Medium | player | to message friends and people at my table | i can talk to people while playing | as a player, i want to message friends and people at my table, so that i can talk to people while playing. | NFR3, NFR7, NFR10, NFR11 | done when players can message friends and use table chat. | E14 | Open
S22 | handle afk players | 2 | High | active player | inactive players to get sat out or removed | the game does not get stuck | as a active player, i want inactive players to get sat out or removed, so that the game does not get stuck. | NFR3, NFR5, NFR9, NFR11 | done when players can be marked afk if they dont do anything. | E15 | Open
S23 | clean up empty tables | 2 | Medium | administrator | empty or inactive tables to get cleaned up | the lobby does not fill with old tables | as a administrator, i want empty or inactive tables to get cleaned up, so that the lobby does not fill with old tables. | NFR5, NFR11 | done when old empty tables should eventually get deleted. | E15 | Open
S24 | fill seats with bots | 1 | Medium | player | bots to fill empty seats | i can play when not enough people are online | as a player, i want bots to fill empty seats, so that i can play when not enough people are online. | NFR5, NFR8, NFR11 | done when bots can play poker and make legal moves. | E16 | Open
S25 | play only bots | -- | Medium | host | to make a table with only bots | i can practice by myself | as a host, i want to make a table with only bots, so that i can practice by myself. | NFR8, NFR9, NFR10 | done when players can start games with bots. | E16 | Open
S26 | watch a game | 2 | Low | user | to watch a table without taking a seat | i can watch friends or learn | as a user, i want to watch a table without taking a seat, so that i can watch friends or learn. | NFR7, NFR9, NFR10 | done when people can watch games without playing. | E17 | Open
S27 | make a private table | 1 | Low | host | to make a private table and invite friends | only invited people can join | as a host, i want to make a private table and invite friends, so that only invited people can join. | NFR1, NFR2, NFR7, NFR11 | done when private tables need an invite to join. | E18 | Open
S28 | manage users and tables | 13 | High | administrator | to manage users tables and games | i can moderate the app | as a administrator, i want to manage users tables and games, so that i can moderate the app. | NFR2, NFR7, NFR11 | done when admins can view users and tables and moderate things. | E19 | Open
S29 | get daily chips | 1 | Low | registered player | to get a daily chip reward | i can keep playing after losing chips | as a registered player, i want to get a daily chip reward, so that i can keep playing after losing chips. | NFR6, NFR11 | done when players can claim free chips sometimes. | E20 | Open
S30 | get chips from ads | 1 | Low | player | to get chips for watching an ad | i can refill my chip balance | as a player, i want to get chips for watching an ad, so that i can refill my chip balance. | NFR6, NFR11 | done when players can get chips after watching an ad. | E21 | Open
S31 | buy virtual chips | 2 | Low | registered player | to buy virtual chips | i can keep playing higher buy in games | as a registered player, i want to buy virtual chips, so that i can keep playing higher buy in games. | NFR6, NFR7, NFR11 | done when players can buy fake chips but cant turn them into real money. | E21 | Open
S32 | earn xp and achievements | 3 | Low | registered player | to earn xp and achievements | i have goals to work toward | as a registered player, i want to earn xp and achievements, so that i have goals to work toward. | NFR6, NFR11 | done when players can earn xp and achievements. | E22 | Open
S33 | seasonal leaderboards | 1 | Low | competitive player | leaderboards to reset by season | there is new competition | as a competitive player, i want leaderboards to reset by season, so that there is new competition. | NFR6, NFR11 | done when the game can have different seasons. | E12 | Open
S34 | choose bot difficulty | -- | Low | player | to choose how hard the bots are | i can practice at different levels | as a player, i want to choose how hard the bots are, so that i can practice at different levels. | NFR8, NFR9 | done when bots can have different difficulty levels. | E16 | Open
S35 | change the theme | 2 | Low | player | to change the game theme | i can change how the game looks | as a player, i want to change the game theme, so that i can change how the game looks. | NFR9, NFR10 | done when players can pick different themes. | E23 | Open
S36 | join tournaments | 2 | Low | player | to join poker tournaments | i can play through elimination rounds | as a player, i want to join poker tournaments, so that i can play through elimination rounds. | NFR5, NFR6, NFR8, NFR11 | done when tournaments should work with blinds, eliminations, and winners. | E24 | Open
S37 | use a bot api | 5 | Low | authorized developer | to use a documented bot api | approved bots can join allowed games | as a authorized developer, i want to use a documented bot api, so that approved bots can join allowed games. | NFR1, NFR2, NFR5, NFR8, NFR11 | done when the api should require login and have rules for how it can be used. | E25 | Open
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Logging in and out is barely worth 1 point
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Seeing a simple disclaimer is not worth any points. That is just a simple HTML without any code.
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If you already have play as normal player, then playing as a guest is just a simple variation of that.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If 'picking an avatar' means uploading an image then it could be worth 3 points. Otherwise it is 1 or 2 points (at most).
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Any story with 8+ is dangerous territory, they are hard to estimate. Consider breaking it into smaller tasks
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You are overestimating by a LOT. Seeing your own hand is barely 1 point.
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Seeing poker rules is not worth a single point, it is just a static page without any programming or logic
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hints are about 3 points, if those hints are very complex I can be persuaded to say it is 5. But it is just simple percentages, like in Texas Holdem Tv tournaments, then 3 is already too much
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just browsing for a table is a read operation that is 2 points and NOT 8.
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You already have Browse tables on S10, then filtering is just a matter of turning the display off on some of them.
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is not a story, this is part of S6. Or should a person playing not have live updates?
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Create a table is a C operation for a CRUD, that is worth 2 points, 3 at max. You are really overestimating the points
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not a story just a part of the definition of done of the user story to create a new player.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Barely worth 1 point.
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Save balance is an update operation for a CRUD.
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is just a simple read operation, 1 point.
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Another simple read operation.
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If you have log in / out, you know how many players are on/off this is just a read operation on the friend list with an online check
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assuming this is a full CRUD, then I am ok with 8 points. If is just a simple send and nothing else, then it would be 2 points
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is at most 2 points, and it could be 1 point depending on the libraries you use for it
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Another simple operation, Delete if a table has no active players
Note on C26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Filling seats is simple and easy. Coding the bot is the complex part. If you have only 1 bot, this is 1 point. If you have multiple bots then it could be 2 points
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is just a specialized version of the previous story. If I can fill seats with bots, then I can fill all seats with bots.
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Watching a game should be 2 points, 3 at max. You already have all the table code for the players to play and see the cards/results. Watching is just displaying with the play logic.
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is just a specialize version of Create Table from an earlier story with added permission.
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I recommend you breaking this into two different stories - Managing Users and Managing Tables, each should be worth about 5-8 points (since a lot of the previous stories already has the same functionalities)
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Barely one point, you are just updating one attribute from the user -- their chip balance
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just clicking or watching an add and getting chips is 1 point; the admin creating the advert would be worth 2, 3 or even 5 points.
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At most 2 points since we are NOT doing real money or credit cards here
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just update operation on the xp gains and which achievements they got
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Simple read operation
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Part of the chosing a bot for the seat story. A combobox to select difficult is not worth any points.
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just joining a tournament, is not worth 13 points. That is just a create/update operation to Join a tournament. The management of the tournament may be another story worth more points
Note on C39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will depend A LOT on how this is done. If you are just using an API then it would be worth 5 points (or even less). If you are coding the bot yourselves then it could be 8 or more.

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description
E1 | Accounts | account registration login and logout
E2 | Age / Legal | the play money and age disclaimer
E3 | Guest Play | letting people try the game without an account
E4 | Profiles | player profiles and avatar choices
E5 | Poker Engine | the main texas holdem rules betting and hand logic
E6 | Learning | rules hand rankings and player hints
E7 | Lobby | finding and filtering public poker tables
E8 | Multiplayer | keeping online players and game state synced
E9 | Tables | creating public poker tables and table settings
E10 | Bankroll | virtual chip balances buy ins wins and losses
E11 | Statistics | tracking player poker statistics
E12 | Leaderboard | ranking players and seasonal competition
E13 | Social | friends and online status
E14 | Messaging | friend messages and table chat
E15 | AFK / Lobby | handling inactive players and abandoned tables
E16 | Bots | computer poker players and bot games
E17 | Spectator | watching games without taking a seat
E18 | Private Tables | invite only poker tables
E19 | Administration | admin moderation and game management
E20 | Rewards | free virtual chip rewards
E21 | Monetization | rewarded ads and virtual chip purchases
E22 | Progression | xp achievements and long term progress
E23 | Customization | table and background themes
E24 | Tournament | tournament style poker games
E25 | Developer Platform | approved developer access for external poker bots
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not really an Epic, this one is either part of a story or as NFR

## NFR
ID | Title | Category | Description | Affects
1 | security | security | passwords should be protected and the site should use https so user info is safe. | some
2 | authorization | authorization | admins should be the only people that can use admin stuff. normal users should not be able to access it. | some
3 | performance | performance | the game should update pretty fast when someone makes a move so other players are not waiting. | some
4 | recovery | availability / recovery | if someone disconnects for a little bit they should be able to come back and still be in the same game. | some
5 | scalability | scalability | the app should still work if there are a lot of tables and players using it at once. | some
6 | data integrity | data integrity | chip amounts should save correctly and players should not randomly gain or lose chips from errors. | some
7 | privacy | privacy | private account information like emails and passwords should not be shown to other players. | some
8 | anti cheat | anti-cheat / fairness | players should not be able to cheat by changing cards or doing moves that are not allowed. | some
9 | accessibility | usability / accessibility | the game should be easy to use and players should be able to understand the buttons and menus. | all
10 | compatibility | compatibility / responsive design | the game should work on common browsers and different screen sizes like phones and computers. | all
11 | maintainability | maintainability / observability | the system should save useful error logs so problems can be figured out when something goes wrong. | all